## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | Install Java 21 JDK and integrate Maven | MUST HAVE | Java 21 / Maven | Renuka | 3- Completed
1 | 1 | US-002 | Create project structure in Project Explorer | MUST HAVE | Maven / IDE | Renuka | 3- Completed
1 | 1 | US-003 | Add Log4j dependency for logging | MUST HAVE | Maven | Renuka | 3- Completed
1 | 1 | US-004 | Add JDBC connection to connect with database | MUST HAVE | MySQL Driver, JDBC | Renuka | 3- Completed
1 | 1 | US-005 | Add Maven Surefire plugin dependency for test execution | MUST HAVE | Maven Surefire | Renuka | 3- Completed
1 | 1 | US-006 | Add JUnit 5 framework for testing | MUST HAVE | JUnit 5, Surefire | Renuka | 3- Completed
2 | 2 | US-007 | Design Database schema (tables, columns) | MUST HAVE | MySQL Workbench / Database | Renuka | 3- Completed
2 | 2 | US-008 | Setup Tomcat Server for API Deployment | MUST HAVE | Apache Tomcat, WAR Packaging | Renuka | 3- Completed
2 | 2 | US-009 | Setup Postman for API Testing | MUST HAVE | Postman | Renuka | 3- Completed
2 | 2 | US-010 | Implement Account Management Engine (CRUD APIs) | MUST HAVE | JDBC, Database schema, Tomcat | Renuka | 3- Completed
2 | 2 | US-011 | Implement Customer Management Engine (CRUD APIs) | MUST HAVE | JDBC, Database schema, Tomcat | Renuka | 3- Completed
3 | 3 | US-012 | Implement Transaction Deposit API | MUST HAVE | JDBC, Database schema | Renuka | 3- Completed
3 | 3 | US-013 | Implement Transaction Withdrawal API | MUST HAVE | JDBC, Database schema | Renuka | 3- Completed
3 | 3 | US-014 | Implement Transfer Transaction API | MUST HAVE | JDBC, Database schema | Renuka | 3- Completed
3 | 3 | US-015 | Update Account Balance after Transaction | MUST HAVE | JDBC, Database schema | Renuka | 3- Completed
3 | 3 | US-016 | Get All Transactions by Account Number | MUST HAVE | JDBC, Database schema | Renuka | 3- Completed
4 | 4 | US-017 | User gets Email Notification for Deposit, Withdrawal, Transfer | MUST HAVE | SMTP dependency (JavaMail) | Renuka | 3- Completed
4 | 4 | US-018 | User can download all transactions of a specific account as an Excel file. | MUST HAVE |  | Renuka | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 79 | 42 | 24 | 11 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T1 | Install Java 21 JDK and integrate Maven | 2025-08-13 | 2025-08-13 | Renuka | Setup | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T2 | Create project structure in Project Explorer | 2025-08-14 | 2025-08-14 | Renuka | Setup | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3 | Add Log4j dependency for logging | 2025-08-15 | 2025-08-15 | Renuka | Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T4 | Add JDBC connection to connect with database | 2025-08-16 | 2025-08-16 | Renuka | Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T5 | Add Maven Surefire plugin dependency for test execution | 2025-08-17 | 2025-08-17 | Renuka | Setup | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T6 | Add JUnit 5 framework for testing | 2025-08-18 | 2025-08-18 | Renuka | Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T7 | Design Database schema (tables, columns) | 2025-08-19 | 2025-08-20 | Renuka | Development | Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T8 | Setup Tomcat Server for API Deployment | 2025-08-21 | 2025-08-21 | Renuka | Setup | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T9 | Setup Postman for API Testing | 2025-08-22 | 2025-08-23 | Renuka | Testing | Completed | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T10 | Implement Account Management Engine (CRUD APIs) | 2025-08-24 | 2025-08-26 | Renuka | Development | Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T11 | Implement Customer Management Engine (CRUD APIs) | 2025-08-27 | 2025-08-29 | Renuka | Development | Completed | 7 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T12 | Implement Transaction Deposit API | 2025-08-30 | 2025-08-31 | Renuka | Development | Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T13 | Implement Transaction Withdrawal API | 2025-09-01 | 2025-09-02 | Renuka | Development | Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T14 | Implement Transfer Transaction API | 2025-09-03 | 2025-09-04 | Renuka | Development | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T15 | Update Account Balance after Transaction | 2025-09-05 | 2025-09-05 | Renuka | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T16 | Get All Transactions by Account Number | 2025-09-06 | 2025-09-07 | Renuka | Development | Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T17 | Implement Email Notification for Deposit, Withdrawal, Transfer | 2025-09-08 | 2025-09-10 | Renuka | Integration | Completed | 4 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | T18 | User can download all transactions of a specific account as an Excel file. | 2025-10-03 | 2025-10-06 | Renuka | Development | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | T19 | Implement Frontend Modules | 2025-10-09 | 2025-10-13 | Renuka | Development | Completed | 7 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Wednesday | Introduction to program and project details – Banking Activity Simulation | Understood overall project goals and features
1 | Thursday | Discussed project environment – Java, JDK 21, Maven, and technology stack | Understood required technologies and tools
1 | Friday | Discussed project structure – Controllers, Service, DAO layers | Created initial folder structure in project explorer
1 | Monday | Planned installation of JDK and Maven setup | Installed JDK 21 and integrated Maven successfully
1 | Tuesday | Maven build demo and verification | Build executed successfully (mvn clean install)
1 | Wednesday | Discussed adding Log4j dependency | Learned purpose of logging and integrated Log4j
1 | Thursday | Demo of Log4j and discussion on JDBC basics | Understood database connectivity using JDBC
1 | Friday | Discussed exception handling, JDBC–MySQL integration, and collections | Learned exception management and JDBC queries
1 | Monday | JDBC connection demo and testing | Successfully established JDBC–MySQL connection
1 | Tuesday | Discussion about JUnit test cases | Understood importance of testing and test structure
1 | Wednesday | Demo on writing and running JUnit test cases | Implemented basic JUnit tests and verified results
2 | Thursday | Discussed about data model – tables creation for Accounts, Customers, and Transactions | Understood table design and relationships; created schema in code
2 | Friday | Demo on creating database tables | Tested and verified successful table creation in MySQL
2 | Monday | Discussed about Account Management System | Started implementation of account module
2 | Tuesday | Discussed CRUD operations for Account APIs | Planned Create, Read, Update, Delete API structure
2 | Wednesday | Discussed about Tomcat server setup and Postman testing | Learned to deploy and test REST APIs
2 | Thursday | Demo of Account Management System APIs and resolved issues | Debugged and verified account CRUD endpoints
2 | Tuesday | Demo of Customer Management System API progress and issue resolution | Implemented and tested Customer API with fixes
2 | Wednesday | Discussed Customer Management System CRUD operations | Understood design and validation rules for customer data
2 | Thursday | Demo and discussion of errors in code | Fixes applied for validation and logic issues
2 | Friday | Demo and review of working APIs | Verified both Account and Customer APIs end-to-end
3 | Monday | Discussed transaction flow | Started working on transaction module design
3 | Tuesday | Discussed how to implement deposit and withdrawal functionalities | Began implementation of transaction logic
3 | Wednesday | Demos on deposit and withdrawal APIs | Tested and verified basic transaction operations
3 | Thursday | Continued demos and debugging transaction issues | Improved transaction validation and balance updates
3 | Friday | Discussed SMTP email alerts after transactions | Planned email integration using SMTP
3 | Tuesday | Updates regarding ongoing tasks and queries | Cleared implementation doubts
3 | Wednesday | Demo on SMTP email functionality | Tested email alerts for deposit and withdrawal
3 | Thursday | Doubts and demos on email sending feature | Debugged email configuration issues
3 | Friday | Demos and clarifications on transaction and email flow | Verified email notifications and transaction flow end-to-end
4 | Tuesday | Doubts and demos for final phase testing | Prepared for integration testing
4 | Friday | Demos, doubts, and discussion on final task to store transaction details in sheets | Implemented export functionality and validated data format
4 | Monday | Final task demo and discussion of remaining doubts | Completed final testing and project wrap-up
4 | Thursday | Discussed frontend design and final demo PPTs | Worked on frontend development.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-08-13 | 2025-08-27 | Renuka Bondapalli | 2025-08-13 | 2025-08-27 |  | Completed
2 | 2 | 2025-08-28 | 2025-09-11 | Renuka Bondapalli | 2025-08-28 | 2025-09-11 |  | Completed
3 | 3 | 2025-09-15 | 2025-09-29 | Renuka Bondapalli | 2025-09-15 | 2025-09-26 |  | Completed
4 | 4 | 2025-09-30 | 2025-10-10 | Renuka Bondapalli | 2025-09-13 | 2025-09-13 |  | Completed
5
6
7