## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Development of the new transfer feature is in progress. The service layer logic is being implemented to ensure data consistency during the multi-step transaction.
1 | Renuka Bondapalli | 2025-09-05 | Maven build failed due to missing dependency: log4j-core. Application couldn’t start. | Sprint 1 | Renuka Bondapalli | Configuration | Added log4j-core dependency in pom.xml and re-ran mvn clean install. | 2025-09-05 | Closed | Verified: Build successful after adding dependency.
2 | Renuka Bondapalli | 2025-09-06 | JDBC connection failure: "No suitable driver found" error during AccountDAO initialization. | Sprint 1 | Renuka Bondapalli | Configuration | Updated pom.xml to include MySQL connector dependency and fixed DB URL in DBConnection.java. | 2025-09-06 | Closed | Tested successfully with valid DB credentials.
3 | Renuka Bondapalli | 2025-09-08 | JUnit tests not executing: "No tests found" reported by Surefire plugin. | Sprint 1 | Renuka Bondapalli | Testing | Added JUnit 5 dependency with correct scope and updated maven-surefire-plugin version. | 2025-09-08 | Closed | Unit tests discovered and executed successfully.
4 | Renuka Bondapalli | 2025-09-10 | CRUD API for Account returning HTTP 500 due to null pointer exception in AccountService. | Sprint 2 | Renuka Bondapalli | Logical | Fixed null check in AccountServiceImpl and added validation utility before calling DAO. | 2025-09-10 | Closed | Verified with Postman – account created successfully.
5 | Renuka Bondapalli | 2025-09-12 | CustomerControllerTest failing: expected 400 Bad Request but actual 404 Not Found on null account number. | Sprint 2 | Renuka Bondapalli | Testing | Added explicit validation for null/empty account number in controller layer with @RequestParam check. | 2025-09-12 | Closed | All related JUnit test cases passed.
6 | Renuka Bondapalli | 2025-09-14 | SQL Exception: "Unknown column 'modified_on' in 'field list'" when calling the /deposit endpoint. The AccountDAO.updateAccountBalance method SQL query references a non-existent database column. | Sprint 3 | Renuka Bondapalli | Logical | Fix: Removed the modified_on = CURRENT_TIMESTAMP clause from the SQL query in the updateAccountBalance method to align the code with the actual database schema. | 2025-09-15 | Closed | The fix was verified by retesting the deposit API call in Postman. The 500 Internal Server Error was resolved, and the transaction was processed successfully.
7 | Renuka Bondapalli | 2025-09-24 | Email Notification defect: Deposit API processed successfully but email not sent to customer. SMTP configuration missing. | Sprint 3 | Renuka Bondapalli | Configuration | Added SMTP configuration in application.properties and integrated JavaMailSender in EmailService. | 2025-09-25 | Closed | Verified: Emails triggered successfully for deposit, withdrawal, and transfer.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others